## Crew work hours
|  | SAFETY, HEALTH, ENVIRONMENT AND QUALITY MANAGEMENT SYSTEM CARGO HOLD CLEANING WORK PLAN using DASIC for Dirty Cargo Residues REPORTING FORMS MANUAL | [47 empty] | Memo : Cargo Operations Date : 25 February 2021 Rev : 1.0 App By : BMM
CARGO HOLD CLEANING WORK PLAN
TYPICAL OPERATION
| 0:30 | 1:00 | 1:30 | 2:00 | 2:30 | 3:00 | 3:30 | 4:00 | 4:30 | 5:00 | 5:30 | 6:00 | 6:30 | 7:00 | 7:30 | 8:00 | 8:30 | 9:00 | 9:30 | 10:00 | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00 | 16:30 | 17:00 | 17:30 | 18:00 | 18:30 | 19:00 | 19:30 | 20:00 | 20:30 | 21:00 | 21:30 | 22:00 | 22:30 | 23:00 | 23:30 | 24:00 | Total Hours Worked | REMARKS
Chief Officer | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 10
2nd Officer | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 10
3rd Officer | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10
2/Engr | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 10
3/Engr | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 10
4/Engr | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | [10 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10
Bosun | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 12
A/B 0-4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 12
A/B 4-8 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 12
A/B 8-12 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 12
O/S A | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 12
O/S B | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 12
Fitter | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 12
Oiler 0-4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 12
Oiler 4-8 | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 12
Wiper 8-12 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 12
Messman | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [10 empty] | 12
No. of available crew for hold cleaning | [12 empty] | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine
NOTE:
1. The above is the minimum crew available for cargo hold cleaning. Fitter can be added if on board. Off-duty Engineers and Messman can be utilized also.
2. After departure discharge port work hours must be adjusted to allow rest for the affected deck crew.
3. Duty officer is instructed to record on this sheet the worked hours of each crew and he is empowered to stop the crew from working if the crew is verified to be in near violation of his rest hours.
4. Working crew must alternate when taking a break for lunch or tea .
5. Above applies when applying slip coat or lime coat.
LEGEND:
|  | BRIDGE WATCH | [5 empty] | ENGINE WATCH
|  | GALLEY JOB | [5 empty] | CAN BE UTILIZED FOR HOLD CLEANING
|  | IF ON BOARD | [5 empty] | AVAILABLE CREW FOR HOLD CLEANING
Time
Note on B5: Master: TIME

## 1st day cleaning
|  | SAFETY, HEALTH, ENVIRONMENT AND QUALITY MANAGEMENT SYSTEM CARGO HOLD CLEANING WORK PLAN using DASIC for Dirty Cargo Residues REPORTING FORMS MANUAL | [48 empty] | Memo : Cargo Operations Date : 25 February 2021 Rev : 1.0 App By : BMM
| CARGO HOLD CLEANING WORK PLAN | [8 empty] | Previous cargo:
TYPICAL OPERATION
Steps | Description | 0:30 | 1:00 | 1:30 | 2:00 | 2:30 | 3:00 | 3:30 | 4:00 | 4:30 | 5:00 | 5:30 | 6:00 | 6:30 | 7:00 | 7:30 | 8:00 | 8:30 | 9:00 | 9:30 | 10:00 | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00 | 16:30 | 17:00 | 17:30 | 18:00 | 18:30 | 19:00 | 19:30 | 20:00 | 20:30 | 21:00 | 21:30 | 22:00 | 22:30 | 23:00 | 23:30 | 24:00 | Total Hours Worked | REMARKS
1 | Toolbox meeting | [12 empty] | 0.5 | [35 empty] | 0.5
2 | Preparation of hold cleaning equipment | [13 empty] | 0.5 | 0.5 | [33 empty] | 1
3 | Forecastle deck washing | [15 empty] | 0.5 | [32 empty] | 0.5
4 | Hatch cover and coaming washing - H1 | [16 empty] | 0.5 | [31 empty] | 0.5
5 | Deck washing - H1 | [16 empty] | 0.5 | 0.5 | [30 empty] | 1
6 | Hold seawater washing - H1 | [17 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [27 empty] | 2
7 | Transferring equipment to next hold | [21 empty] | 0.5 | [26 empty] | 0.5
8 | Cleaning bilges (removing >2mm size residues)- H1 | [21 empty] | 0.5 | 0.5 | [25 empty] | 1 | Alternate bilge suction with H2
9 | Hatch cover and coaming washing - H2 | [17 empty] | 0.5 | [30 empty] | 0.5
10 | Deck washing - H2 | [18 empty] | 0.5 | 0.5 | [28 empty] | 1
11 | Hold seawater washing - H2 | [22 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [22 empty] | 2
12 | Transferring equipment to next hold | [26 empty] | 0.5 | [21 empty] | 0.5
13 | Cleaning bilges (removing >2mm size residues)- H2 | [26 empty] | 0.5 | 0.5 | [20 empty] | 1 | Alternate bilge suction with H3
14 | Hatch cover and coaming washing - H3 | [22 empty] | 0.5 | [25 empty] | 0.5
15 | Deck washing - H3 | [23 empty] | 0.5 | 0.5 | [23 empty] | 1
16 | Hold seawater washing - H3 | [27 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [17 empty] | 2
17 | Transferring equipment to next hold | [31 empty] | 0.5 | [16 empty] | 0.5
18 | Cleaning bilges (removing >2mm size residues)- H3 | [31 empty] | 0.5 | 0.5 | [15 empty] | 1
19 | Hatch cover and coaming washing - H4 | [27 empty] | 0.5 | [20 empty] | 0.5
20 | Deck washing - H4 | [28 empty] | 0.5 | 0.5 | [18 empty] | 1
21 | Hatch cover and coaming washing - H5 | [30 empty] | 0.5 | [17 empty] | 0.5
22 | Deck washing - H5 | [31 empty] | 0.5 | 0.5 | [15 empty] | 1
23 | Compass deck to poop deck washing | [31 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [13 empty] | 2
24 | Securing of hold cleaning equipment | [35 empty] | 0.5 | [12 empty] | 0.5
| No. of available crew for hold cleaning | [12 empty] | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine

## 2nd day cleaning
|  | SAFETY, HEALTH, ENVIRONMENT AND QUALITY MANAGEMENT SYSTEM CARGO HOLD CLEANING WORK PLAN using DASIC for Dirty Cargo Residues REPORTING FORMS MANUAL | [48 empty] | Memo : Cargo Operations Date : 25 February 2021 Rev : 1.0 App By : BMM
CARGO HOLD CLEANING WORK PLAN
TYPICAL OPERATION
Steps | Description | 0:30 | 1:00 | 1:30 | 2:00 | 2:30 | 3:00 | 3:30 | 4:00 | 4:30 | 5:00 | 5:30 | 6:00 | 6:30 | 7:00 | 7:30 | 8:00 | 8:30 | 9:00 | 9:30 | 10:00 | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00 | 16:30 | 17:00 | 17:30 | 18:00 | 18:30 | 19:00 | 19:30 | 20:00 | 20:30 | 21:00 | 21:30 | 22:00 | 22:30 | 23:00 | 23:30 | 24:00 | Total Hours Worked | REMARKS
1 | Toolbox meeting | [12 empty] | 0.5 | [35 empty] | 0.5
2 | Preparation of hold cleaning equipment | [13 empty] | 0.5 | [34 empty] | 0.5
3 | Hold seawater washing - H4 | [14 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [30 empty] | 2
4 | Transferring equipment to next hold | [18 empty] | 0.5 | [29 empty] | 0.5
5 | Cleaning bilges (removing >2mm size residues)- H4 | [18 empty] | 0.5 | 0.5 | [28 empty] | 1
6 | Hold seawater washing - H5 | [19 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [25 empty] | 2
7 | Removing equipment from hold - H5 | [23 empty] | 0.5 | [24 empty] | 0.5
8 | Cleaning bilges (removing >2mm size residues)- H5 | [23 empty] | 0.5 | 0.5 | [23 empty] | 1
9 | Preparation of DASIC & chemical cleaning equipment | [24 empty] | 0.5 | 0.5 | [22 empty] | 1
10 | DASIC (2 units) chemical washing recirculation 2/3 height drop - H1 FWD | [26 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [18 empty] | 2
11 | Adjusting DASIC (2units) to 1/3 height | [30 empty] | 0.5 | [17 empty] | 0.5
12 | DASIC (2 units) chemical washing recirculation 1/3 height drop - H1 FWD | [31 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [13 empty] | 2
13 | Transferring equipment to AFT | [35 empty] | 0.5 | [12 empty] | 0.5
14 | DASIC (2 units) chemical washing recirculation 2/3 height drop - H1 AFT | [36 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 2
15 | Adjusting DASIC (2units) to 1/3 height | [40 empty] | 0.5 | [7 empty] | 0.5
16 | DASIC (2 units) chemical washing recirculation 1/3 height drop - H1 AFT | [41 empty] | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  | 2
17 | Transferring equipment to next hold | [45 empty] | 0.5 | 0.5 |  | 1
18 | Pumping out washwater - H1 | [45 empty] | 0.5 |  |  | 0.5
19 | Preparing new chemical mixture | [47 empty] | 0.5 | 0.5
| No. of available crew for hold cleaning | [12 empty] | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 3deck, 1engine | 3deck, 1engine | 3deck, 1engine | 3deck, 1engine | 3deck, 1engine | 3deck, 1engine | 3deck, 1engine | 3deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck
|  | 0:30 | 1:00 | 1:30 | 2:00 | 2:30 | 3:00 | 3:30 | 4:00 | 4:30 | 5:00 | 5:30 | 6:00 | 6:30 | 7:00 | 7:30 | 8:00 | 8:30 | 9:00 | 9:30 | 10:00 | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00 | 16:30 | 17:00 | 17:30 | 18:00 | 18:30 | 19:00 | 19:30 | 20:00 | 20:30 | 21:00 | 21:30 | 22:00 | 22:30 | 23:00 | 23:30 | 24:00
| Chief Officer | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 10
| 2nd Officer | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 10
| 3rd Officer | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10
| 2/Engr | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 10
| 3/Engr | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 10
| 4/Engr | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | [10 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10
| Bosun | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10
| A/B 0-4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 10
| A/B 4-8 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 12
| A/B 8-12 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 12
| O/S A | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10
| O/S B | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 10
| Fitter | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 12
| Oiler 0-4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 12
| Oiler 4-8 | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 12
| Wiper 8-12 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 12
| Messman | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [10 empty] | 12
Note on C26: Master: TIME

## 3rd day cleaning
|  | SAFETY, HEALTH, ENVIRONMENT AND QUALITY MANAGEMENT SYSTEM CARGO HOLD CLEANING WORK PLAN using DASIC for Dirty Cargo Residues REPORTING FORMS MANUAL | [48 empty] | Memo : Cargo Operations Date : 25 February 2021 Rev : 1.0 App By : BMM
CARGO HOLD CLEANING WORK PLAN
TYPICAL OPERATION
Steps | Description | 0:30 | 1:00 | 1:30 | 2:00 | 2:30 | 3:00 | 3:30 | 4:00 | 4:30 | 5:00 | 5:30 | 6:00 | 6:30 | 7:00 | 7:30 | 8:00 | 8:30 | 9:00 | 9:30 | 10:00 | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00 | 16:30 | 17:00 | 17:30 | 18:00 | 18:30 | 19:00 | 19:30 | 20:00 | 20:30 | 21:00 | 21:30 | 22:00 | 22:30 | 23:00 | 23:30 | 24:00 | Total Hours Worked | REMARKS
1 | DASIC (2 units) chemical washing recirculation 2/3 height drop - H2 FWD | 0.5 | 0.5 | 0.5 | 0.5 | [44 empty] | 2
2 | Adjusting DASIC (2units) to 1/3 height |  |  |  |  | 0.5 | [43 empty] | 0.5
3 | DASIC (2 units) chemical washing recirculation 1/3 height drop - H2 FWD | [5 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [39 empty] | 2
4 | Transferring equipment to AFT | [9 empty] | 0.5 | 0.5 | [37 empty] | 1
5 | DASIC (2 units) chemical washing recirculation 2/3 height drop - H2 AFT | [11 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [33 empty] | 2
6 | Adjusting DASIC (2units) to 1/3 height | [15 empty] | 0.5 | [32 empty] | 0.5
7 | DASIC (2 units) chemical washing recirculation 1/3 height drop - H2 AFT | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [28 empty] | 2
8 | Transferring equipment to next hold | [20 empty] | 0.5 | 0.5 | [26 empty] | 1
9 | Pumping out washwater - H2 | [20 empty] | 0.5 | [27 empty] | 0.5
10 | Preparing new chemical mixture | [22 empty] | 0.5 | [25 empty] | 0.5
11 | DASIC (2 units) chemical washing recirculation 2/3 height drop - H3 FWD | [23 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [21 empty] | 2
12 | Adjusting DASIC (2units) to 1/3 height | [27 empty] | 0.5 | [20 empty] | 0.5
13 | DASIC (2 units) chemical washing recirculation 1/3 height drop - H3 FWD | [28 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 2
14 | Transferring equipment to AFT | [32 empty] | 0.5 | 0.5 | [14 empty] | 1
15 | DASIC (2 units) chemical washing recirculation 2/3 height drop - H3 AFT | [34 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [10 empty] | 2
16 | Adjusting DASIC (2units) to 1/3 height | [38 empty] | 0.5 | [9 empty] | 0.5
17 | DASIC (2 units) chemical washing recirculation 1/3 height drop - H3 AFT | [39 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [5 empty] | 2
18 | Transferring equipment to next hold | [43 empty] | 0.5 | 0.5 |  |  |  | 1
19 | Pumping out washwater - H3 | [43 empty] | 0.5 |  |  |  |  | 0.5
20 | Preparing new chemical mixture | [45 empty] | 0.5 |  |  | 0.5
21 | DASIC (2 units) chemical washing recirculation 2/3 height drop - H4 FWD | [46 empty] | 0.5 | 0.5 | 1
| No. of available crew for hold cleaning | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 2deck | 2deck | 2deck | 2deck | 5deck | 5deck | 5deck | 5deck | 5deck | 5deck | 5deck | 5deck | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck
|  | 0:30 | 1:00 | 1:30 | 2:00 | 2:30 | 3:00 | 3:30 | 4:00 | 4:30 | 5:00 | 5:30 | 6:00 | 6:30 | 7:00 | 7:30 | 8:00 | 8:30 | 9:00 | 9:30 | 10:00 | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00 | 16:30 | 17:00 | 17:30 | 18:00 | 18:30 | 19:00 | 19:30 | 20:00 | 20:30 | 21:00 | 21:30 | 22:00 | 22:30 | 23:00 | 23:30 | 24:00
| Chief Officer | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 10
| 2nd Officer | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 10
| 3rd Officer | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10
| 2/Engr | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 10
| 3/Engr | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 10
| 4/Engr | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | [10 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10
| Bosun | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10
| A/B 0-4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 10
| A/B 4-8 | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 10
| A/B 8-12 | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10
| O/S A | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10
| O/S B | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 10
| Fitter | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 12
| Oiler 0-4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 12
| Oiler 4-8 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 12
| Wiper 8-12 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 12
| Messman | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [10 empty] | 12
Note on C28: Master: TIME

## 4th day cleaning
|  | SAFETY, HEALTH, ENVIRONMENT AND QUALITY MANAGEMENT SYSTEM CARGO HOLD CLEANING WORK PLAN using DASIC for Dirty Cargo Residues REPORTING FORMS MANUAL | [48 empty] | Memo : Cargo Operations Date : 25 February 2021 Rev : 1.0 App By : BMM
CARGO HOLD CLEANING WORK PLAN
TYPICAL OPERATION
Steps | Description | 0:30 | 1:00 | 1:30 | 2:00 | 2:30 | 3:00 | 3:30 | 4:00 | 4:30 | 5:00 | 5:30 | 6:00 | 6:30 | 7:00 | 7:30 | 8:00 | 8:30 | 9:00 | 9:30 | 10:00 | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00 | 16:30 | 17:00 | 17:30 | 18:00 | 18:30 | 19:00 | 19:30 | 20:00 | 20:30 | 21:00 | 21:30 | 22:00 | 22:30 | 23:00 | 23:30 | 24:00 | Total Hours Worked | REMARKS
1 | DASIC (2 units) chemical washing recirculation 2/3 height drop - H4 FWD | 0.5 | 0.5 | [46 empty] | 1
2 | Adjusting DASIC (2units) to 1/3 height |  |  | 0.5 | [45 empty] | 0.5
3 | DASIC (2 units) chemical washing recirculation 1/3 height drop - H4 FWD |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | [41 empty] | 2
4 | Transferring equipment to AFT | [7 empty] | 0.5 | 0.5 | [39 empty] | 1
5 | DASIC (2 units) chemical washing recirculation 2/3 height drop - H4 AFT | [9 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [35 empty] | 2
6 | Adjusting DASIC (2units) to 1/3 height | [13 empty] | 0.5 | [34 empty] | 0.5
7 | DASIC (2 units) chemical washing recirculation 1/3 height drop - H4 AFT | [14 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [30 empty] | 2
8 | Transferring equipment to next hold | [18 empty] | 0.5 | 0.5 | [28 empty] | 1
9 | Pumping out washwater - H4 | [18 empty] | 0.5 | [29 empty] | 0.5
10 | Preparing new chemical mixture | [20 empty] | 0.5 | [27 empty] | 0.5
11 | DASIC (2 units) chemical washing recirculation 2/3 height drop - H5 FWD | [21 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [23 empty] | 2
12 | Adjusting DASIC (2units) to 1/3 height | [25 empty] | 0.5 | [22 empty] | 0.5
13 | DASIC (2 units) chemical washing recirculation 1/3 height drop - H5 FWD | [26 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [18 empty] | 2
14 | Transferring equipment to AFT | [30 empty] | 0.5 | 0.5 | [16 empty] | 1
15 | DASIC (2 units) chemical washing recirculation 2/3 height drop - H5 AFT | [32 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 2
16 | Adjusting DASIC (2units) to 1/3 height | [36 empty] | 0.5 | [11 empty] | 0.5
17 | DASIC (2 units) chemical washing recirculation 1/3 height drop - H5 AFT | [37 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [7 empty] | 2
18 | Removing equipment from hold - H5 | [41 empty] | 0.5 | [6 empty] | 0.5
19 | Pumping out washwater - H5 | [41 empty] | 0.5 | [6 empty] | 0.5
20 | Securing of hold cleaning equipment | [42 empty] | 0.5 | 0.5 |  |  |  |  | 1
| No. of available crew for hold cleaning | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 1deck, 1engine | 2deck | 2deck | 2deck | 2deck | 5deck | 5deck | 5deck | 5deck | 5deck | 5deck | 5deck | 5deck | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck, 1engine | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck | 2deck
|  | 0:30 | 1:00 | 1:30 | 2:00 | 2:30 | 3:00 | 3:30 | 4:00 | 4:30 | 5:00 | 5:30 | 6:00 | 6:30 | 7:00 | 7:30 | 8:00 | 8:30 | 9:00 | 9:30 | 10:00 | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00 | 16:30 | 17:00 | 17:30 | 18:00 | 18:30 | 19:00 | 19:30 | 20:00 | 20:30 | 21:00 | 21:30 | 22:00 | 22:30 | 23:00 | 23:30 | 24:00
| Chief Officer | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 10
| 2nd Officer | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 10
| 3rd Officer | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10
| 2/Engr | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 10
| 3/Engr | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 10
| 4/Engr | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | [10 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10
| Bosun | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  |  | 8
| A/B 0-4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 10
| A/B 4-8 | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 10
| A/B 8-12 | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10
| O/S A | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  |  | 8
| O/S B | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 10
| Fitter | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 12
| Oiler 0-4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 12
| Oiler 4-8 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 12
| Wiper 8-12 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 12
| Messman | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [10 empty] | 12
Note on C27: Master: TIME

## 5th day cleaning
|  | SAFETY, HEALTH, ENVIRONMENT AND QUALITY MANAGEMENT SYSTEM CARGO HOLD CLEANING WORK PLAN using DASIC for Dirty Cargo Residues REPORTING FORMS MANUAL | [48 empty] | Memo : Cargo Operations Date : 25 February 2021 Rev : 1.0 App By : BMM
CARGO HOLD CLEANING WORK PLAN
TYPICAL OPERATION
Steps | Description | 0:30 | 1:00 | 1:30 | 2:00 | 2:30 | 3:00 | 3:30 | 4:00 | 4:30 | 5:00 | 5:30 | 6:00 | 6:30 | 7:00 | 7:30 | 8:00 | 8:30 | 9:00 | 9:30 | 10:00 | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00 | 16:30 | 17:00 | 17:30 | 18:00 | 18:30 | 19:00 | 19:30 | 20:00 | 20:30 | 21:00 | 21:30 | 22:00 | 22:30 | 23:00 | 23:30 | 24:00 | Total Hours Worked | REMARKS
1 | Toolbox meeting | [12 empty] | 0.5 | [35 empty] | 0.5
2 | Preparation of hold cleaning equipment | [13 empty] | 0.5 | [34 empty] | 0.5
3 | Hold seawater rinsing - H1 | [14 empty] | 0.5 | [33 empty] | 0.5
4 | Fresh water rinsing - H1 | [15 empty] | 0.5 | 0.5 | [31 empty] | 1
5 | Transferring equipment to next hold | [15 empty] | 0.5 | [32 empty] | 0.5
6 | Hold seawater rinsing - H2 | [16 empty] | 0.5 | [31 empty] | 0.5
7 | Fresh water rinsing - H2 | [17 empty] | 0.5 | 0.5 | [29 empty] | 1
8 | Transferring equipment to next hold | [17 empty] | 0.5 | [30 empty] | 0.5
9 | Hold seawater rinsing - H3 | [18 empty] | 0.5 | [29 empty] | 0.5
10 | Fresh water rinsing - H3 | [19 empty] | 0.5 | 0.5 | [27 empty] | 1
11 | Transferring equipment to next hold | [19 empty] | 0.5 | [28 empty] | 0.5
12 | Hold seawater rinsing - H4 | [20 empty] | 0.5 | [27 empty] | 0.5
13 | Fresh water rinsing - H4 | [21 empty] | 0.5 | 0.5 | [25 empty] | 1
14 | Transferring equipment to next hold | [21 empty] | 0.5 | [26 empty] | 0.5
15 | Cleaning bilges - H1 | [20 empty] | 0.5 | 0.5 | [26 empty] | 1 | Alternate bilge pumping with H5
16 | Hold seawater rinsing - H5 | [22 empty] | 0.5 | [25 empty] | 0.5 | Alternate bilge pumping with H1
17 | Fresh water rinsing - H5 | [23 empty] | 0.5 | 0.5 | [23 empty] | 1
18 | Removing equipment from hold - H5 | [23 empty] | 0.5 | [24 empty] | 0.5
19 | Cleaning bilges - H2 | [22 empty] | 0.5 | 0.5 | [24 empty] | 1
20 | Cleaning bilges - H3 | [24 empty] | 0.5 | 0.5 | [22 empty] | 1
21 | Cleaning bilges - H4 | [26 empty] | 0.5 | 0.5 | [20 empty] | 1
22 | Cleaning bilges - H5 | [28 empty] | 0.5 | 0.5 | [18 empty] | 1
23 | Drying up holds, finalizing | [22 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [13 empty] | 6.5
24 | Securing of hold cleaning equipment | [35 empty] | 0.5 | [12 empty] | 0.5
| No. of available crew for hold cleaning | [12 empty] | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 6deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine | 5deck, 1engine
Note:
If chemical cleaning is not required then skip the steps related to chemical washing.